## Slide 1: Five Year CIP Program FY 24/25 - FY 28/29
March 2024

## Slide 2: Projected 5 Year CIP Overview
Chart: 5 Year CIP (in $ Millions)
| FY 24/25 | FY 25/26 | FY 26/27 | FY 27/28 | FY 28/29
Water CIP Total | 6.955 | 3.85 | 7.333 | 15.5772 | 7.025
Sewer CIP Total | 0.525 | 0.05 | 0.5 | 9.7 | 12
Total Water - $40.7M
Total Sewer - $22.8M
Total CIP - $63.5M

## Slide 3: Water 5 Year CIP by Driver (in $ Millions)
Chart: 
| Easement Requirement | Improvements/Upgrades | Planning | Rehab/Replacement | Source of Supply - Resiliency/Savings
 | 0.125 | 11.364 | 1 | 17.9413 | 10.31

## Slide 4: Water 5 Year CIP by Asset Type ( in $ Millions)
Chart: 
| Headquarters | Pipelines | Planning | Pressure Reducing Stations | Pump Stations | Reservoirs | Source of Supply | Valves | Vehicles/Equip.
5 Year CIP | 6.1 | 12.3202 | 1 | 0.45 | 10.21 | 1.65 | 5.4 | 1.46 | 2.15

## Slide 5: Sewer 5 Year CIP by Asset Type (in $ Millions)
Chart: 
| Lift stations | Sewer Lines | Sewer LS Generators
5 Year CIP | 10.5 | 11.75 | 0.525

## Slide 6: Sewer 5 Year CIP by Driver (in $ Millions)
Chart: 
| Additional Capacity - Current Limitations | Additional Capacity - New Development | Rehab/Replacement
 | 9.55 | 10.5 | 2.725

## Slide 7: Proposed Fiscal Year Project Summary
Water Fund 60 & 62
Wastewater Fund 52 & 53
FY 24/25: 1 Project
FY 25/26: 1 Project
FY 26/27: 1 Project
FY 27/28: 4 Projects
FY 28/29: 3 Projects
FY 24/25: 12 Projects
FY 25/26: 9 Projects
FY 26/27: 14 Projects
FY 27/28: 11 Projects
FY 28/29: 6 Projects

## Slide 8: Projected 10 Year CIP Overview
Chart: 10 Year CIP (in $ Million)
| FY 24/25 | FY 25/26 | FY 26/27 | FY 27/28 | FY 28/29 | FY 29/30 | FY 30/31 | FY 31/32 | FY 32/33 | FY 33/34
Water CIP Total | 6.955 | 3.85 | 7.333 | 15.5772 | 7.025 | 6.5 | 3.455 | 16.85 | 0.68 | 1.2
Sewer CIP Total | 0.525 | 0.05 | 0.5 | 9.7 | 12 | 5.65 | 2 | 0.1 | 0.65 | 0
Total Water - $69.4M
Total Sewer - $31.2M
Total CIP - $100.6M

## Slide 9: Water Projects FY 24/25

## Slide 10: Water and Wastewater Master Plan
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD | $500,000 | $500,000 |  |  |  | $1,000,000
Scope of Work: Develop Long-range Water and Sewer System Master Plan. Includes Constructing system hydraulic model utilizing latest software technology to evaluate and identify system deficiencies and solutions based on updated demand projections and system operations.
Project Rationale: The project will provide the District with a master plan of project improvements for long-term planning, prioritization, and funding for water and wastewater infrastructure needs.

## Slide 11: West Lilac, Rancho Amigos and Dentro De Lomas Pump Stations (600013)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600013 | $3,400,000 |  |  |  |  | $3,400,000
Scope of Work: Install three (3) pump stations to provide water to the Hutton-Turner-Gopher Tank zones.
Project Rationale: Required operational project to deliver water to the District's southern pressure zones absent SDCWA supply.

## Slide 12: SDCWA Connections 1, 8, 9, and 10 Acquisition
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD | $500,000 |  |  |  |  | $500,000
Scope of Work: Purchase/acquire facilities and property associated with existing SDCWA connections 1, 8, 9, and 10.
Project Rationale: This is a condition of detachment.

## Slide 13: Gopher Skid Pump Station
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD | $710,000 |  |  |  |  | $710,000
Scope of Work: Replace the temporary pump skid with a permanent solution.
Project Rationale: Required operational flexibility to move water within the southern zone absent SDCWA connections.

## Slide 14: FPUD Maravilla to RMWD Maravilla (Morro Tank)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD | $210,000 |  |  |  |  | $210,000
Scope of Work: Install 750 LF of C900 PVC pipeline to connect FPUD and RMWD potable water systems.
Project Rationale: Operational flexibility to source water into the Morro Tank zone providing additional capacity from Morro Reservoir to the District's southern pressure zones.

## Slide 15: FPUD Olive Hill to RMWD Olive Hill (Morro Reservoir)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD | $235,000 |  |  |  |  | $235,000
Scope of Work: Install 840 LF of C900 PVC Pipeline to connect FPUD and RMWD potable water systems.
Project Rationale: Operational flexibility to source water into the Morro Reservoir providing additional capacity to the District's southern pressure zones.

## Slide 16: La Canada Pipeline Replacement and Pressure Reduction
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD | $100,000 | $700,000 |  |  |  | $800,000
Scope of Work: Replace 4,000 LF of pipeline along La Canada from Hillrise Rd. to Via Monserate and install two (2) new pressure reducing stations.
Project Rationale: The project will prevent future costs associated with leaks or main breaks and reduce service interruptions. This alignment of pipeline has experienced eight (8) main breaks within the last five (5) years.

## Slide 17: Isolation Valve Installation Program (600009)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600009 | $100,000 | $500,000 | $180,000 | $500,000 | $180,000 | 
 | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | 
 | $500,000 | $180,000 | $500,000 | $180,000 | $500,000 | $3,320,000
Scope of Work: Replace isolation valves district-wide that have exceeded their useful life.
Project Rationale: The project will reduce the number of customers impacted by service interruptions due to leaks and main breaks and reduce repair time due to valves that don't fully seal. The Project will also replace valves in the broken or open positions.

## Slide 18: Pressure Reducing Stations (600007)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600007 | $150,000 | $150,000 | $150,000 |  |  | $450,000
Scope of Work: Install previously purchased pressure reducing stations district-wide in areas of high pressure.
Project Rationale: The project will reduce high-pressure zones to extend the useful life of water infrastructure and reduce damage associated with main line breaks.

## Slide 19: Camino Del Rey Waterline Relocation (600026)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600026 | $100,000 | $25,000 |  |  |  | $125,000
Scope of Work: Relocate existing water and sewer infrastructure due to the County of San Diego's Road Improvement Project.
Project Rationale: The project will ensure continuity of service during the County-initiated construction project and upgrade water facilities.

## Slide 20: Manual Transfer Switches (600058)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600058 | $200,000 |  |  |  |  | $200,000
Scope of Work: Install manual transfer switches at Morro Hills Pump Station, Rainbow Hills Pump Station, and Vallecitos Pump Station.
Project Rationale: The project will ensure the safety of District staff when switching to backup power during emergencies.

## Slide 21: District Headquarters (300008)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
300008 | $600,000 | $500,000 | $1,000,000* | $4,000,000* | $0 | $ 6,100,000
Scope of Work: Repair and replace necessary facilities for on-going operations and explore options for long-term District facilities plan with the recently re-established Ad-Hoc committee.
Project Rationale: The project will fund roof and HVAC upgrades in the Admin Building in FY24/25 to maintain adequate facilities in the near-term and explore feasibility of a long-term facilities solution of either re-development of the existing site and relocation of District facilities or extending the useful life of existing facilities through significant upgrades. Facilities support day-to-day administration and operations of the District.
*Assumes a significant investment will occur starting in FY26/27 to either fund major activities associated with re-development of the site (EIR and entitlements) or existing facilities rehabilitation.

## Slide 22: Sewer Projects FY 24/25

## Slide 23: Rancho Monserate, Rancho Viejo, and HQ B-Plant Emergency Generators (530023)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
530023 | $525,000* |  |  |  |  | $525,000
Scope of Work: This project proposes to in-kind replacements of the obsolete emergency generators at Rancho Monserate, Rancho Viejos, and HQ B-Plant lift stations.
Project Rationale: The project will provide a backup power source for critical sewer infrastructure. Existing equipment hhas exceeded its useful life.
*Grant funding dependent

## Slide 24: Pipeline Replacement Projects Years 2-10

## Slide 25: Gird to West Lilac Pipeline Rehabilitation (600085)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600085 |  | $125,000 | $1,235,000 |  |  | $1,360,000
Scope of Work: Pipeline is currently abandoned in place with end caps at the North and South. To avoid environmental impacts and permitting issues, Cure-in-Place (CIPP) technologies will be utilized.
Project Rationale: With this waterline out of service more customers are affected by shutdowns as well as it limits operational flexibility to move water throughout the system.

## Slide 26: Gopher Canyon Water Pipeline Improvements (600045)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600045 |  |  | $138,000 | $2,760,000 |  | $2,898,000
Scope of Work: Install multiple pipe segments within Gopher Canyon Road, Margale Lane, and Integrity Ct.
Project Rationale: The pipeline is past its useful life. Within this alignment there are several dead ends as well as sections of pipeline crossing private property. The proposed project would create a looped system.

## Slide 27: Roy Line Extension (600075)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600075 |  |  | $150,000 | $2,000,000 |  | $2,150,000
Scope of Work: Replace 1,056 feet of 6-inch pipe on Emerald Hills Road near North River Road as identified in the Condition Assessment as High Risk.
Project Rationale: The project will prevent future costs associated with leaks or main breaks and reduce service interruptions.

## Slide 28: FPUD Bonita Valle to RMWD Del Valle (Morro Tank)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  | $170,000 |  |  | $170,000
Scope of Work: Install 600 LF of C900 to connect FPUD and RMWD potable water systems.
Project Rationale: The project will assist in transporting critical water supply to Morro Tank. Once fully disconnected from the SDCWA this project will be reassessed.

## Slide 29: FPUD Olive Hill to RMWD Spanish Spur (Morro Reservoir)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  | $155,000 |  |  | $155,000
Scope of Work: Install 550 LF of C900 to connect FPUD and RMWD potable water systems.
Project Rationale: The project will assist in transporting critical water supply to Morro Reservoir. Once fully disconnected from the SDCWA this project will be reassessed.

## Slide 30: FPUD Burma Rd. to RMWD Sleeping Indian (Morro Tank)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  | $345,000 |  |  | $345,000
Scope of Work: Install 1,217 LF of C900 to connect FPUD and RMWD potable water systems.
Project Rationale: The project will assist in transporting critical water supply to Morro Tank. Once fully disconnected from the SDCWA this project will be reassessed.

## Slide 31: FPUD Sanchez Zone to RMWD Northside Zone (Rainbow Hills Reservoir)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  | $60,000 |  |  | $60,000
Scope of Work: Install 180 LF of C900 to connect FPUD and RMWD potable water systems.
Project Rationale: The project will assist in critical water supply to Rainbow Hills Reservoir. Once fully disconnected from the SDCWA this project will be reassessed.

## Slide 32: Eagle's Perch Water Pipeline Improvements (600043)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600043 |  |  |  | $96,000 | $1,920,000 | $2,016,000
Scope of Work: Replace and relocate water pipelines in difficult-to-access easements to a new alignment within a roadway and private driveway.
Project Rationale: The pipeline has exceeded its useful life. Within this alignment there are several dead ends as well as sections of pipeline crossing private property. The proposed project would also remove a District asset from private property.

## Slide 33: Rice Canyon Main Replacement (600061)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600061 |  |  |  | $1,500,000 |  | $1,500,000
Scope of Work: Replace 2,149 feet of 8-inch pipe on Rice Canyon Road, north of the Rice Canyon tank.
Project Rationale: This pipeline has exceeded its useful life and has had seven (7) main breaks. Any main breaks in this area cause catastrophic damage to the road resulting in full lane closures for repairs.

## Slide 34: Pala Mesa Fairways Community (600067)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600067 |  |  |  | $71,250 | $2,500,000 | $2,571,250
Scope of Work: Replace 1,500 feet of 8-inch pipe identified by the Condition Assessment as High Risk.
Project Rationale: This pipeline has exceeded its useful life and has experienced 14 mainline leaks.

## Slide 35: Sarah Ann Entire Community and Fallbrook Oaks Force Main, and Manhole Replacement (600068 and 530018)
 | Planned Expenditures |  |  |  |  | 
Project | Year 5 (FY 28/29) | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Total
600068 | $200,000 | $4,000,000 |  |  |  | $4,200,000
530018 |  | $1,650,000 |  |  |  | $1,650,000
Scope of Work: Replace pumps, suction piping, manholes, electrical, motor controls, and 800 feet of 6-inch force main at Fallbrook Oaks Lift Station. Additionally, the 8-inch water line will be replaced within Sarah Ann community.
Project Rationale: The existing lift station is obsolete. The existing force main alignment runs adjacent to channel. The existing pipeline for the entire community has experienced 26 mainline leaks.

## Slide 36: Thibido Water Main Replacement (600066)
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
600066 | $700,000 |  |  |  |  | $700,000
Scope of Work: Replace 940 feet of 6-inch pipe identified in the Condition Assessment as High Risk.
Project Rationale: The project will prevent future costs associated with leaks or main breaks and reduce service interruptions. Ingress/egress does not accommodate vehicles or heavy equipment.

## Slide 37: North Feeder and Rainbow Hills Water Line Replacements (600051)
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
600051 |  | $150,000 | $1,850,000 |  |  | $2,400,000
Scope of Work: Replace 3,788 feet of 30-inch and 27-inch pipelines that are severely corroded using CIPP technologies. In addition, the project would add three (3) new isolation valves.
Project Rationale: The pipeline is at the end of its useful life. The pipeline runs under the highway making access for any repairs or maintenance difficult.

## Slide 38: Water Pump Stations/Electrical Upgrades Years 2-10

## Slide 39: Lookout Mountain Pump Station Electrical Upgrades and New Emergency Generator (600050)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600050 |  | $500,000 | $3,000,000 |  |  | $3,500,000
Scope of Work: Enclosed facility with upgraded pumps, motor control, electrical components, transfer switch, and a new emergency generator.
Project Rationale: The project will ensure reliability of critical water infrastructure during emergencies. Existing equipment is obsolete.

## Slide 40: Weese WTP Permanent Emergency Interconnect Pump Station (600008)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600008 |  |  |  |  | $1,725,000 | $1,725,000
Scope of Work: Install a pump station to pull water from Oceanside's Weese WTP into the District's southern zone.
Project Rationale: Required operational flexibility to move water without SDCWA connections within the southern zone.

## Slide 41: Gomez Pump Station Electrical Upgrades
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  | $100,000 | $1,000,000 |  | $1,100,000
Scope of Work: Upgrade motor controls, breakers, relays, and wiring to replace obsolete system.
Project Rationale: Existing equipment is obsolete.

## Slide 42: Vallecitos Pump Station Replacement (600040)
Scope of Work: Replace the existing pump station, which was constructed in 1978.
Project Rationale: Existing equipment is reaching the end of its useful life and requires replacement.
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY29/30) | Year7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
600040 | $500,000 | $1,400,000 |  |  |  | $1,900,000

## Slide 43: Morro Pump Station Rehabilitation (600084)
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
600084 | $300,000 | $1,225,000 |  |  |  | $1,525,000
Scope of Work: Retrofit the existing pump station facility, replace pumps and motor controls.
Project Rationale: Station is near the end of its useful life and provides operational flexibility to move the water in the Southern zone.

## Slide 44: Detachment Requirements Years 2-5

## Slide 45: SDCWA Connections 3, 6, 7, and 11 Interim Decommissioning
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  | $350,000 |  |  |  | $350,000
Scope of Work: Interim decommissioning at SDCWA connections 3, 6, 7, 11, and 12.
Project Rationale: Requirement of detachment from SDCWA.

## Slide 46: SDCWA Connections 3, 6, 7, 11, and 12 Permanent Decommissioning
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  |  | $1,650,000 |  | $1,650,000
Scope of Work: Permanent decommissioning of SDCWA connections 3, 6, 7, 11, and 12.
Project Rationale: Requirement of detachment from SDCWA.

## Slide 47: Sewer Lift Stations/Electrical Upgrades Years 2-10

## Slide 48: School House Lift Station
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  |  | $500,000 | $10,000,000 | $10,500,000
Scope of Work: This project proposes construction of a new lift station to help address current and projected build-out flows.
Project Rationale: The project is intended to offset higher demand at Lift Station-1 which has limited capacity. The proposed Lift Station would be needed to additional development. If needed, the project would be funded with future capacity fees.

## Slide 49: Sewer Pipeline/CIPP Years 2-10

## Slide 50: North River Road Sewer Capacity Expansion
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  | $50,000 | $500,000 | $9,000,000 |  | $9,550,000
Scope of Work: This project proposes to upsize a 15-inch sewer pipeline to a 21-inch sewer pipeline along North River Road from Via Puerta del Sol to Wilshire Road.
Project Rationale: The project is intended to address capacity of an undersized system.

## Slide 51: CIPP 2,000 LF of 8-inch VCP near Pala Mesa/Palomar (530019)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
530019 |  |  |  | $100,000 | $1,000,000 | $1,100,000
Scope of Work: This project proposes to install 2,000 to 4,000 linear feet CIPP lining on an existing 8-inch vitrified clay pipe (VCP) and to raise or relocate manholes throughout the golf course.
Project Rationale: The project will extend the useful life of the facility and reduce ongoing maintenance costs. Inflow and infiltrations (I&I) will be reduced.

## Slide 52: Lake Garden CIPP Lining
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  |  | $100,000 | $1,000,000 | $1,100,000
Scope of Work: This project proposes to install about ~2,800 linear feet of CIPP lining and to line manholes.
Project Rationale: The project will extend the useful life of the facility and reduce ongoing maintenance costs. I&I will be reduced.

## Slide 53: CIPP Lining
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD | $1,000,000 |  |  |  |  | $1,000,000
Scope of Work: This project proposes to install CIPP lining district-wide.
Project Rationale: The project will extend the useful life of facilities and reduce ongoing maintenance costs. I&I will be reduced.

## Slide 54: Old River Road between LS-1 and LS-2
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD | $3,000,000 |  |  |  |  | $3,000,000
Scope of Work: This project proposes to convert a gravity main to a force main and upsize to a 21-inch pipe between LS-1 and LS-2 on Old River Road.
Project Rationale: The project is intended to address capacity of an undersized system.

## Slide 55: Gopher Canyon CIPP
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD |  | $2,000,000 |  |  |  | $2,000,000
Scope of Work: This project proposes to install CIPP lining along a segment of sewer alignment on Gopher Canyon Road includes lining manholes and replacing frames and covers.
Project Rationale: The project will extend the useful life of the facility and reduce ongoing maintenance costs. I&I will be reduced.

## Slide 56: Oakcliff CIPP
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD |  |  | $100,000 | $650,000 |  | $750,000
Scope of Work: This project proposes CIPP lining of approximately 2,000 linear feet of sewer main along Oakcliff drive.
Project Rationale: The project will extend the useful life of the facility and reduce ongoing maintenance costs. I&I will be reduced.

## Slide 57: Tank Maintenance and Other Projects Years 2-10

## Slide 58: Morro Chemical Tanks
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  | $150,000 | $1,500,000 |  | $1,650,000
Scope of Work: Install two (2) new ammonia and chlorine storage chemical tanks at the Morro Reservoir.
Project Rationale: The project will establish an adequate supply of chemical storage to treat varying water chemistry as-needed.

## Slide 59: Rainbow Heights Tank Interior/Exterior Coating (4M Gallons)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  | $1,000,000 |  |  | $1,000,000
Scope of Work: Restore interior and exterior coating at the Rainbow Heights Tank.
Project Rationale: The project will extend the useful life of the tank.

## Slide 60: Gopher Canyon Tank Interior/Exterior Coating (4M Gallons)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  |  | $1,050,000 |  | $1,050,000
Scope of Work: Restore interior and exterior coatings at the Gopher Canyon Tank.
Project Rationale: The project will extend the useful life of the tank.

## Slide 61: Turner Tank Interior/Exterior Coating (4M Gallons)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
TBD |  |  |  |  | $1,102,500 | $1,102,500
Scope of Work: Restore interior and exterior coatings at the Turner Tank.
Project Rationale: The project will extend the useful life of the tank.

## Slide 62: Hutton Tank Interior/Exterior Coating (4M Gallons)
Scope of Work: Restore interior and exterior coatings at the Hutton Tank.
Project Rationale: The project will extend the useful life of the tank.
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD | $1,157,652 |  |  |  |  | $1,157,652

## Slide 63: Rice Canyon Tank Interior/Exterior Coating (4M Gallons)
Scope of Work: Restore interior and exterior coatings at the Rice Canyon Tank.
Project Rationale: The project will extend the useful life of the tank.
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD |  | $1,215,506 |  |  |  | $1,215,506

## Slide 64: Replace Liners and Floating Covers at Morro, Rainbow Hills, and North Reservoirs
Scope of Work: Replace liners and floating covers at Morro Reservoir, Rainbow Hills Reservoir, and North Reservoir.
Project Rationale: Potable water reservoirs are required by the state to be covered. The existing covers and lining are approaching the end of their useful life.
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD |  |  | $14,000,000 |  |  | $14,000,000

## Slide 65: Vallecitos Tank Interior/Exterior Coating (500k Gallons)
Scope of Work: Restore interior and exterior coating at the Vallecitos Tank.
Project Rationale: The project will extend the useful life of the tank.
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD |  |  |  |  | $1,407,100 | $1,407,100

## Slide 66: Upper Lookout Tank Interior/Exterior Coating (500k Gallons)
Scope of Work: Restore interior and exterior coatings at the Upper Lookout Tank.
Project Rationale: The project will extend the useful life of the tank.
 | Planned Expenditures |  |  |  |  | 
Project | Year 6 (FY 29/30) | Year 7 (FY 30/31) | Year 8 (FY 31/32) | Year 9 (FY 32/33) | Year 10 (FY 33/34) | Total
TBD |  |  |  |  | $200,000 | $200,000

## Slide 67: Questions?