## Slide 1: CIP Program Year 1 Projects FY 24/25
August 2024

## Slide 3: Water Projects FY 24/25

## Slide 4: West Lilac, Rancho Amigos and Dentro De Lomas Pump Stations (600013)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600013 | $3,400,000 |  |  |  |  | $3,400,000
Scope of Work: Install three (3) pump stations to provide water to the Hutton-Turner-Gopher Tank zones.
Project Rationale: Required operational project to deliver water to the District's southern pressure zones absent SDCWA supply.
JULY 2024
JUNE 2025
OCT 2024
Construction
Construction Complete
Notice of Completion
DEC 2024

## Slide 5: District Headquarters (300008)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
300008 | $500,000 | $500,000 | $1,000,000 | $4,000,000 |  | $ 6,000,000
Scope of Work: Repair and replace necessary facilities for on-going operations and explore options for long-term District facilities plan with the recently re-established Ad-Hoc committee.
Project Rationale: The project will fund roof and HVAC upgrades in the Admin Building in FY24/25 to maintain adequate facilities in the near-term and explore feasibility of a long-term facilities solution of either re-development of the existing site and relocation of District facilities or extending the useful life of existing facilities through significant upgrades. Facilities support day-to-day administration and operations of the District.
JULY 2024
JUNE 2025
Ad Hoc Committee Meeting
Design Completion
FEB 2025

## Slide 6: Pressure Reducing Stations (600007)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600007 | $150,000 | $150,000 | $150,000 |  |  | $450,000
Scope of Work: Install previously purchased pressure reducing stations district-wide in areas of high pressure.
Project Rationale: The project will reduce high-pressure zones to extend the useful life of water infrastructure and reduce damage associated with main line breaks.
JULY 2024
JUNE 2025
Ongoing
Ongoing

## Slide 7: Isolation Valve Installation Program (600009)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600009 | $100,000 | $500,000 | $180,000 | $500,000 | $180,000 | $1,460,000
Scope of Work: Replace isolation valves district-wide that have exceeded their useful life.
Project Rationale: The project will reduce the number of customers impacted by service interruptions due to leaks and main breaks and reduce repair time due to valves that don't fully seal. The Project will also replace valves in the broken or open positions.
JULY 2024
JUNE 2025
Ongoing
Ongoing

## Slide 8: Manual Transfer Switches (600058)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600058 | $200,000 |  |  |  |  | $200,000
Scope of Work: Install manual transfer switches at Morro Hills Pump Station, Rainbow Hills Pump Station, and Vallecitos Pump Station.
Project Rationale: The project will ensure the safety of District staff when switching to backup power during emergencies.
JULY 2024
JUNE 2025
Review Design
Out
for Bid
AUG 2024
NOV 2024
JAN 2025
Install

## Slide 9: Camino Del Rey Waterline Relocation (600026)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600026 | $100,000 | $25,000 |  |  |  | $125,000
Scope of Work: Relocate existing water and sewer infrastructure due to the County of San Diego's Road Improvement Project.
Project Rationale: The project will ensure continuity of service during the County-initiated construction project and upgrade water facilities.
JULY 2024
JUNE 2025
Ongoing
Analysis
Finalize
coordination w/County

## Slide 10: SDCWA Connections 1, 8, 9, and 10 Acquisition (600088)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600088 | $500,000 |  |  |  |  | $500,000
Scope of Work: Purchase/acquire facilities and property associated with existing SDCWA connections 1, 8, 9, and 10.
Project Rationale: This is a condition of detachment.
JULY 2024
JUNE 2025
DEC 2024
REVIEW
Final
Agreement

## Slide 11: SDCWA Connections 3, 6, 7, and 11 Interim Decommissioning
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600089 | $200,000 |  |  |  |  | $200,000
Scope of Work: Interim decommissioning at SDCWA connections 3, 6, 7, and 11.
Project Rationale: Requirement of detachment from SDCWA.
Ongoing
Ongoing
JULY 2024
JUNE 2025

## Slide 12: FPUD Maravilla to RMWD Maravilla (Morro Tank) (600091)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600091 | $210,000 |  |  |  |  | $210,000
Scope of Work: Install 750 LF of C900 PVC pipeline to connect FPUD and RMWD potable water systems.
Project Rationale: Operational flexibility to source water into the Morro Tank zone providing additional capacity from Morro Reservoir to the District's southern pressure zones.
JULY 2024
JUNE 2025
Scope
Design
Design
Complete
FEB 2025
MAR 2025
Construction

## Slide 13: FPUD Olive Hill to RMWD Olive Hill (Morro Reservoir) (600092)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600092 | $235,000 |  |  |  |  | $235,000
Scope of Work: Install 840 LF of C900 PVC Pipeline to connect FPUD and RMWD potable water systems.
Project Rationale: Operational flexibility to source water into the Morro Reservoir providing additional capacity to the District's southern pressure zones.
Scope
Design
Complete
Design
Construction
JULY 2024
FEB 2025
MAR 2025
JUNE 2025

## Slide 14: La Canada Pipeline Replacement and Pressure Reduction (600093)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600093 | $100,000 | $700,000 |  |  |  | $800,000
Scope of Work: Replace 4,000 LF of pipeline along La Canada from Hillrise Rd. to Via Monserate and install two (2) new pressure reducing stations.
Project Rationale: The project will prevent future costs associated with leaks or main breaks and reduce service interruptions. This alignment of pipeline has experienced eight (8) main breaks within the last five (5) years.
Scope
Design Complete
Design
Construction
JULY 2024
FEB 2025
MAR 2025
JUNE 2025

## Slide 15: Gopher Skid Pump Station (600094)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600094 | $710,000 |  |  |  |  | $710,000
Scope of Work: Replace the temporary pump skid with a permanent solution.
Project Rationale: Required operational flexibility to move water within the southern zone absent SDCWA connections.
JULY 2024
JUNE 2025
MAR 2025
Design
Completion
Design
Construction
Scope

## Slide 16: Water and Wastewater Master Plan (600090)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
600090 | $100,000 | $750,000 |  |  |  | $850,000
Scope of Work: Develop Long-range Water and Sewer System Master Plan. Includes Constructing system hydraulic model utilizing latest software technology to evaluate and identify system deficiencies and solutions based on updated demand projections and system operations.
Project Rationale: The project will provide the District with a master plan of project improvements for long-term planning, prioritization, and funding for water and wastewater infrastructure needs.
JULY 2024
JUNE 2025
RFP
Posting
Award
JAN 2025
MAR 2025

## Slide 17: Sewer Projects FY 24/25

## Slide 18: Rancho Monserate, Rancho Viejo, and HQ B-Plant Emergency Generators (530023)
 | Planned Expenditures |  |  |  |  | 
Project | Year 1 (FY 24/25) | Year 2 (FY 25/26) | Year 3 (FY 26/27) | Year 4 (FY 27/28) | Year 5 (FY 28/29) | Total
530023 | $525,000* |  |  |  |  | $525,000
Scope of Work: This project proposes to in-kind replacements of the obsolete emergency generators at Rancho Monserate, Rancho Viejos, and HQ B-Plant lift stations.
Project Rationale: The project will provide a backup power source for critical sewer infrastructure. Existing equipment has exceeded its useful life.
*Grant funding dependent
Scope
Design
Design
Complete
JULY 2024
JUNE 2025
OCT 2024
FEB 2025
APR 2025
Construction

## Slide 19: Questions?